## Slide 1: Employment Priority Axis Evaluation
Onur TATAR
Assistant EU Expert
PMMEU

## Slide 2
TOPICS
CONTENT OF THE EVALUATION
FINDINGS - Grants
FINDINGS – Programs and Technical Assistance
FINDINGS – Programme Management
PROGRESS
SITUATION OF HRD OP

## Slide 3
CONTENT OF THE EVALUATION
  Promoting Women Employment (PWE) – İŞKUR
    Technical Assistance and Grant
  Promoting Youth Employment (PYE) – İŞKUR
    Technical Assistance and Grant
  Public Employment Services (PES) – İŞKUR
    Technical Assistance and Supply
  Promoting Registered Employment (PRE) – SGK
    Technical Assistance, Grant and Supply

## Slide 4
PROGRESS
Start
02.05.2013 Kick-off meeting
Background studies and stakeholders
30.05.2013 Discussion with stakeholders
Over 20 meetings with evaluation experts
Interviews and meetings
Ankara, Samsun, Van focus groups
Finalisation
04.10.2013 Final Meeting with Stakeholders in Limak Ambassadore Hotel
Short report was sent to İŞKUR and SGK in 06.10.2013 for their comments
Interviews with HRD OS, OB staff

## Slide 5
FINDINGS - Grants
Growth center approach was found effective
15 Growth Centers Hinterlands
(Other provinces)
  PWE : % 46 % 54
  PYE : % 61 % 39
  PRE : % 82 % 18
  Total : % 58 % 42

## Slide 6
FINDINGS - Grants
Relation between Needs and grant benefits:
Growth Centers | SEDI Index | Allocation (€)
Van | -1,391 | 4.064.695,45
Kars | -1,267 | 359.083,42
Batman | -1,204 | 1.492.152,50
Diyarbakır, Şanlıurfa | -0,964 | 3.462.326,74
Erzurum | -0,790 | 1.838.374,64
Kastamonu | -0,675 | 981.880,65
Trabzon | -0,559 | 5.170.369,97
Elazığ, Malatya | -0,559 | 4.669.951,30
Samsun | -0,417 | 9.507.157,30
Kayseri, Sivas | -0,376 | 7.478.409,20
Kahramanmaraş | -0,338 | 4.900.580,64
Gaziantep | -0,315 | 1.133.053,27

## Slide 7
FINDINGS - Grants
Relation between the amount of grant applications and approvals
Growth Centers | SEDI Index | Applications | Success Rate
Van | -1,391 | 405 | 6,4%
Kars | -1,267 | 83 | 3,6%
Batman | -1,204 | 106 | 6,6%
Diyarbakır, Şanlıurfa | -0,964 | 171 | 9,9%
Erzurum | -0,790 | 154 | 7,1%
Kastamonu | -0,675 | 109 | 7,3%
Trabzon | -0,559 | 229 | 16,2%
Elazığ, Malatya | -0,559 | 186 | 14,5%
Samsun | -0,417 | 270 | 21,5%
Kayseri, Sivas | -0,376 | 259 | 18,5%
Kahramanmaraş | -0,338 | 147 | 19,0%
Gaziantep | -0,315 | 133 | 10,9%
Ankara, Istanbul | N/A | 172 | 12,8%
Total |  | 2424 | 12,3%

## Slide 8
FINDINGS - Grants
Tendency to plan and implement vocational and technical education activities rather than innovative initiatives
Insufficient experience of Grant beneficiaries on Project management and building up partnerships
Supply side institutions are more devoted to partnership obligations than the demand side
Low concentration on horizontal issues in the projects

## Slide 9
FINDINGS - Grants
Operation Beneficiaries utilises less than expected from the outcomes of grant projects
Insufficient connection between grant programs and Technical Assistance contracts
Inadequate reliable data and difficulties to measure the impacts
Transfer of experience between east and west is insufficient

## Slide 10
FINDINGS - Grants
Increasing the absorbtion capacity
Providing technical assistance to potential beneficiaries
Obligatory partnerships and introducing rigid rules to partnership selection
Suggestions of the Evaluation
Providing technical assistance to operation beneficiaries to promote closer cooperation between them and grant beneficiaries

## Slide 11
Half of the beneficiaries are municipalities, associations and chambers
Activities are implemented at hinterlands
Indicators mostly achieved according to grant beneficiaries‘ self-assessment
Partnerships successful according to beneficiaries
GRANTS
LM survey and analyses welcomed
Client Referral System requires adaptation
Job Clubs represent top result
Gender Mainstreaming training successful
Grant scheme dissemination appreciated
Project successful, offers potential for nation-wide use.
Technical Assistance
PROGRAMS – PROMOTING WOMEN EMPLOYMENT GRANT and TECHNICAL ASSISTANCE
Activity Types (no. of activities) | Frequency | % distribution by group of activities
Development and delivery of vocational and job counselling services (3) | 142 | 23
Development and delivery of training/ re-training on vocational professions (3) | 205 | 33
Promotion and guidance for entrepreneurship (4) | 115 | 19
Support services for women seeking employment (3) | 28 | 5
Awareness and sensitivity raising on women employment (3) | 55 | 9
Field studies and labour market surveys (2) | 57 | 9
Social dialogue and partnership (1) | 13 | 2

## Slide 12
Around 63% applications were from associations municipalities, chambers and public education centers
In self-assessment of beneficiaries PYE seems to be less successful than other programs (in terms of targets)
Training efficiency was under question
PYE
TECHNICAL ASSISTANCE
Design flaw in relation to cooperation with KOSGEB
YES Model developed and introduced
Company agreements: target exceeded
Policy related Action Plans: Low expectations
Problems in composition of TAT, OCU staff continuity
Delaying approvals of OBs
Technical Assistance was understood as a service to be used directly rather than a support tool
PROGRAMS – PROMOTING YOUTH EMPLOYMENT GRANT and TECHNICAL ASSISTANCE
Type of Activity | Frequency | Share (%)
Improving vocational and job skills | 273 | 55
Entrpreneurship education and support | 72 | 14
Counselling - transition from school to work | 109 | 22
Innovative activities related to employability of young people | 45 | 9

## Slide 13
Promoters more experienced
Similar tendency towards „standard“ activities (VET) plus awareness-raising (no predecessor scheme)
Awareness-raising seen as major success
Grant beneficiaries : Small portion of them took support from SGK
PRE
TECHNICAL ASSISTANCE
Good cooperation between parties
Training highly appreciated; trainer corps not utilised
Strategy Paper highly appreciated
Joint database finalised – issues in usage (SGK with Revenue Administration)
Awareness-raising very successful
Field studies useful for analysis of needs
Problem: 21 months not sufficient
PROGRAMS – PROMOTING REGISTERED EMPLOYMENT GRANT and TECHNICAL ASSISTANCE
Chart: 
| Associations | Chambers | Development Agencies | Foundations | Municipality | Organized Industrial Zones | Special Provincial Administrations | TOTAL | Trade Unions | UN Development Programme | Unions | Universities
 | 23.9279 | 26.0516 | 3.9164 | 4.8559 | 3.6399 | 4.6828 | 2.2364 | 5.8745 | 3.6816 | 19.9174 | 1.2157

## Slide 14
No grant component
Out of grant analysis
PES
TECHNICAL ASSISTANCE
«Flagship project», highly praised
Model office Action Plans delivered, trainings delivered
Labour Market Information System requires adaptations and updates
Job and vocational counselling trainings are successful yet their employment situation in doubt
Active Labour Market Policy monitoring is on track
PEVTB assessment delayed
Visibility activities excellent
Policy training good,
Internships questionable
Large scope of the project led to problems with communication, approval decisions, internal procedures
PROGRAMS – PUBLIC EMPLOYMENT SERVICES TECHNICAL ASSISTANCE

## Slide 15
Tendency to plan and implement vocational and technical education activities rather than innovative initiatives
Insufficient experience of Grant beneficiaries on Project management and building up partnerships
Supply side institutions are more devoted to partnership obligations than the demand side
Low concentration on horizontal issues in the projects
Insufficient cooperation between Operation Beneficiaries and Grant Beneficiaries
Inadequate reliable data to measure impacts
GRANTS
TECHNICAL ASSISTANCE
Overall negatives;
  Procedures takes long time, expected outputs are too high; but relatively implementation periods are too short
  Frequent changes of employees in Technical Assistance Teams and operation coordination units
  Low achievements from internship activities
  Low interaction with grant programs
Overall positives;
  Indicators and targets are converged mostly
  HRD OS, Obs, TAT, contractor cooperation was beneficial
  Study visits found to be successful.
PROGRAMS – GRANTS AND TECHNICAL ASSISTANCE OVERALL

## Slide 16
FINDINGS – Related to Programme Management
Application Procedures and Contracting:
Info Days good but late
Implementation Support
TA support provided by HRD OS was successful but better if it was done earlier
Support in application development needed
Evaluation not enough influenced by OBs
Evaluation and contracting periods are long
CFCU was overloaded and required responses were delayed
Some grant schemes still not finalised due to expenditure disagreement
Additional support in regions raised quality
There were problems in procurement processes
Implementation Manual which was prepared by HRD OS was useful but the outcomes could be better if it was prepared earlier

## Slide 17
FINDINGS – Related to Programme Management
Monitoring and Evaluation
Monitoring is focused to technical side in general and content monitoring should be improved
Monitors often lacked practical experience
OBs not enough represented in evaluation teams
G-MIS too late, not obligatory, insufficient data, not used as PM tool
No assessments of grant schemes carried out

## Slide 18
FINDINGS – Related to HRD OP Institutions
Institutional Capacity
İŞKUR
Grant Beneficiaries:
Inadequate understanding of ownership
use of external experts and personnel both in planning and implementation
Coordination and communication improved between staff and institutions
Challenging partner selections but successful outcomes of contributions
Job and vocational Guidance counsellors are employed on the basis of short-term contracts.
experienced difficulties in preserving institutional memory
number of staff was increased.
HRD OS
Staff development was seen but trainings for the new experts increase the already high workload
SGK
Staff turnover is under control
Strategic approach to technical assistance

## Slide 19
SITUATION OF HRD OP
Relevancy
Objectives and activities of HRD OP are still relevant to socio-economic and demographic conditions
Changing migration dynamics
Lack of data of disadvantaged groups
Coherency
HRD OP is perfectly coherent with
National policy and strategies,
EU policy and strategies,
National and EU funding procedures

## Slide 20
THANK YOU