## Slide 1: HRDOP IN IMPLEMENTATION Quick Summary of Achievements
Presented by Project Management Unit
22.11.2013

## Slide 2: Achieved Cornerstones via Ongoing Operations

## Slide 3: List of Ongoing Operations
Measure 1.4: Improving the Quality of Public Employment Services
Measure 2.1: Increasing Enrolment Rates Especially For Girls In Secondary Education
Measure 2.2: Improving the Quality of Vocational and Technical Education in Turkey
Measure 3.1: Promoting Life Long Learning
Measure 3.2: Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Measure 3.2: Increasing Adaptability of Employers and Employees in Tourism Sector
Measure 3.2: Increasing Adaptability of Tradesmen and Craftsmen
Measure 4.1: Facilitating Access of Disadvantaged Higher Education Students to Labour Market Including Scholarship Support
Measure 5.1: Implementation of Human Resources Development Operational Programme
Measure 5.2-5.3:Potential Operation and Grant Beneficiaries, Information and Publicity

## Slide 4: Measure 1.4 Technical Assistance for Improving The Quality of Public Employment Services
Completion of the preparation of Model Office Action Plans in 43 provinces
Completion of trainings regarding Model Office approach at the provincial level to the staff in 43 provinces
Completion of the preparation of a methodology on conducting labour market analyses and delivering the training to the staff of the Beneficiary at the local and central level
Completion of study visits regarding job and vocational guidance services
Publication of guidelines including information on public employment services
http://www.kip.org.tr

## Slide 5: Technical Assistance for Improving The Quality of Public Employment Services (2)
Completion of the design of a model to monitor the active labour market policies provided by the Beneficiary
Completion of an analysis report regarding the increase of effectiveness of Provincial Employment and Vocational Training Boards
Completion of Communication Campaign II
Completion of short films on introduction and selection of occupations
Completion of internships regarding employment policy making in European Agencies and relevant institutions for 20 staff from the Beneficiary and the MoLSS
http://www.kip.org.tr

## Slide 6: Supply for Improving The Quality of Public Employment Services
Provisional acceptance procedures for the supply contract of
Lot 1: Office Furniture has been completed

## Slide 7: Technical Assistance for Improving the Quality of Vocational Education and Training in Turkey
Establishment of working relationships between TAT and counterparts
Identification of social partners and engaging in project.
Assessment of a sample of schools undertaken and production of situation analysis
Commencement of drafting national quality assurance strategy system concept paper.
Developing Self-Evaluation Manual and NQAS Manual
Delivery of trainings for self-evaluation component of NQAS in all 50 pilot institutions.
Preparation of vocational maps in 22 fields and 91 occupational analyses.
http://metek.meb.gov.tr
Measure 2.2

## Slide 8: Supply for Improving the Quality of Vocational Education and Training in Turkey (2)
Three Lots were signed on 19.04.2013 and the implementation started. Provisional acceptance procedures are ongoing
Lot 2 – Farming, Animal Care and Food Processing Equipment
Lot 5 – IT and Office Equipment and Electrical Appliances
Lot 8 – Mechanical Manufacturing Equipment

## Slide 9: Measure 2.1
Provisional Acceptance process for two lots was completed:
Lot 1 - Information Technology Equipment
Lot 3 - White Goods Equipment
Provisional Acceptance process for three lots is ongoing:
Lot 5 - Food Technology Equipment
Lot 6 - Cosmetics And Hair Care Services Equipment
Lot 7 - Food And Beverages Services Equipment (Kitchen)
Supply for Increasing Enrollment Rates Especially for Girls Operation

## Slide 10: Measure 3.1 Supply Contract for Promoting Life Long Learning Operation
Provisional acceptance procedures for the following supply contracts have been completed:
Lot 1: Office Furniture
Lot 2: IT Equipment, Hardware and Software

## Slide 11: Measure 3.2 Technical Asistance for Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Completion of review of the stakeholders in the regions and the previous relevant projects
Preparation of the training need survey in the 15 Growth Centres
Designing and preparation of the best practice survey in the developed Turkish regions
Establishment and maintenance of website

## Slide 12: Supply for Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Two contracts below mentioned were signed and the process of provisional acceptances are ongoing for both contracts:
Lot 1: Office Furniture
Lot 3: Electrical Equipment

## Slide 13: Measure 3.2 Technical Assistance for Increasing Adaptability of Employers and Employees in Tourism Sector
The global-price contract has been signed on 04.11.2013. After selection of the key experts commencement date will be determined by the Project Manager and the implementation phase will start subsequently.

## Slide 14: Supply for Increasing Adaptability of Employers and Employees in Tourism Sector
Provisional acceptance procedures have been completed.
Lot 1: Information, Technologies, Electrical and Electronic Equipment

## Slide 15: Measure 3.2 Supply for Increasing Adaptability of Tradesmen and Craftsmen
Procedures regarding delivery, installation, putting into operation, inspection and testing of the equipments are ongoing.
Lot 1: Office Furniture
Lot 2: IT Equipment
Lot 3: Woodwork Equipment
Lot 4: Industrial Cooking Equipment

## Slide 16: Measure 5.1 Technical Assistance for Implementation of Human Resources Development Operational Programme
  Extension of the project for 9 months
Delivery of the following trainings;
  Introductory trainings for newly recruited staff
  Irregularities, internal control and risk management
  Grant and framework evaluation, tender evaluation
  Hybrid Tendering
  Eligibility of expenditures and rules of payment process
  Financial planning and expenditure verification
  Advanced Budget Evaluation
  Simplified cost option

## Slide 17: Technical Assistance for Implementation of Human Resources Development Operational Programme (2)
Completion of the study visits in order to give an insight on funds management of the country visited and allowing for the members of each unit in IPA MD to exchange experiences on below areas;
  Program management and procurement process
  Project management
  Financial management
  Quality assurance and coordination processes
  IT applications
Establishment and Improvement of G-MIS and MIS
Full time consultancy support to İKGPRO
Evaluation of HRD OP process is on-going

## Slide 18: Supply Contract for Implementation of Human Resources Development Operational Programme
The project has been finalized by issuing the final acceptance certificates. Dates of the final acceptances are as follows:
Lot 1 – 07.05.2013
Lot 2 – 15.05.2013
Lot 3 and Lot 5 – 08.05.2013
Lot 4 – final acceptance procedures are ongoing
Lot 6 – 05.04.2013

## Slide 19: Measure 5.2-5.3 Technical Assistance for Potential Operational and Grant Beneficiaries, Information and Publicity
Extension of the Project for 9 months
Revision of HRD OP Mainstreaming Strategy in line with the comments and feedback of the HRD OS Units and Beneficiaries.
Delivery of an introductory training and Concept Note training to Roma People
Delivery of Training and Direct Expert Support regarding OIS, ToR, Grant Guideline, Operation and Project preparation to Operation Beneficiaries and Operating Structures
PRE-II and PYE-II Concept Note and Full Application Trainings
Conducting of study visit to Denmark about Life Long Learning and Adaptability of Employers and Employees

## Slide 20: Technical Assistance for Potential Operational and Grant Beneficiaries, Information and Publicity (2)
Organization of Info Days in more than twenty cities regarding HRD OP Grant Scheme, EU funds and EU Institutions
Delivery of ‘Information and Visibility’ training to all potential OBs
Organization of Awareness raising activities for the launch of the Call for Operations and also for the launch operation of YURTKUR
Publication and distribution of HRD OP Achievement Book and HRD OP information booklet to 20.000 students
Utilization of ‘Media monitoring’ for our project activities to ensure capturing all occasions where project related news appear in newspapers, TV, radios, etc.
HRD OP Promotional Film is ongoing

## Slide 21: Highlights in Recently Completed Operations

## Slide 22: Measure 1.1 Technical Assistance for Promoting Women Employment
The most successful one of the newly developed methods was women job clubs. Job clubs provide intensive motivation and support for longer-term unemployed people. After 3 weeks of involving in the clubs, 60 % of the participants received a job offer and %50 of the participants has started to work.
Client Referral Network was developed as the most relevant ALMP model for overcoming multiple obstacles for female labor force participation. Several seminars were organized for İŞKUR staff and relevant partner institutions to present, improve and develop the model. Model was tested through trainings and services delivered to women target groups.
      www.kadinistihdami.net

## Slide 23: Measure 1.2 Technical Assistance for Promoting Youth Employment
The most successful activity of the project is the «Youth Entrepreneurship Support Model (YES Model)». The protocol is signed with 20 institutions in order to implement the services envisaged under this model. YES Model is designed with four SERVICE AREAS: “Promotion and Orienteering Area and Awareness Raising Activities”, “Pre-feasibility Check and Evaluation of The Business Idea”, “Support of the Business Plan & Project ” and the “Business Set-Up And Business Financial Development Supports”.
    http://www.gencistihdami.net

## Slide 24: Measure 2.1
The most important activities of the project were:
Providing the incentives to girls such as boots, coats, school bags, stationery equipment for 2000 children
Conducting face to face interviews (house visits) to at least (final target) 3.200 families in 16 pilot provinces by the trained teachers
Conducting trainings for 180 formator teachers about the psychological guidance
http://kizlarinegitimi.meb.gov.tr
Technical Assistance for Increasing Enrollment Rates Especially for Girls

## Slide 25: Measure 3.1 Technical Assistance for Promoting Life Long Learning
The most important activities of the project were:
A Policy Paper, covering all aspects of lifelong learning policy
A draft Law on Coordination of Lifelong Learning
A draft National Strategy and Action Plan, 2014 – 2018
43 Provincial Lifelong Learning Action Plans
An RPL Framework document, five sets of RPL Operational Guidelines and an RPL Implementation Plan
Protocols with TOBB, TİSK and TÜSİAD providing workplace training for 900 teachers
http://hayatboyu.meb.gov.tr

## Slide 26: Measure 4.1 Facilitating Access of Disadvantaged Higher Education Students to Labour Market Including Scholarship Support
20.000 Higher Education Students (10.000 male and 10.000 female) received scholarship in 2012-2013 academic year.
Each student was paid 2080 Turkish Liras for 8 months.
Displaced students from their villages because of terrorism, students in their last credit year who are in poverty or at risk of poverty and selected as eligible scholarship recipients but could not receive scholarship due to the limited budget of DG CHI and orphans.
13.000 Higher Education Students (6.500 male and 6.500 female) will receive scholarship for 2013-2014 academic year.