## Slide 1: HRDOP IN IMPLEMENTATION Quick Summary of Achievements
16.06.2015

## Slide 2: List of Ongoing Operations
Measure 1.1: Woman in Business
Measure 1.3 Promoting Registered Employment through Better Guidance and Inspection-II
Measure 2.1: Increasing Enrolment Rates Especially For Girls In Secondary Education-II
Measure 2.1: Strengthening the Impact of the Conditional Cash Transfer Programme in Turkey for Increasing High School Attendance
Measure 2.2: Improving the Quality of Vocational and Technical Education in Turkey
Measure 2.2: Improving the Quality of VET and Vocational Skills of Young People
Measure 3.2: Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Measure 3.2: Increasing Adaptability of Employers and Employees in Tourism Sector
Measure 3.2: Increasing Adaptability of Tradesmen and Craftsmen
Measure 4.1: Employment and Social Support Services Coordination and Implementation Model for the Integration of Disadvantaged Persons
Measure 4.1: Facilitating Access of Disadvantaged Higher Education Students to Labor Market Including Scholarship Support

## Slide 3: Women in Business Programme
Operation Beneficiary is Turkish Employment Agency. Implemented by EBRD.
Total budget of the programme: 38.000.000 €
The overall objective of the Programme is to promote women's entrepreneurship in Turkey, and women’s participation in business, by assisting women-led small and medium-sized enterprises to access finance, know-how and non-financial business development services.
The purpose of the Programme is to:
  Support women-led small and medium sized enterprises (SMEs) in accessing finance for their sustainable growth and job creation
  Develop sustainable credit mechanisms targeted to women-led SMEs through technical assistance to participating financial institutions
  Support women-owned and women-managed SMEs in accessing know-how, non-financial business development services and networking opportunities.
  Help improve human resources at women-led SMEs.

## Slide 4: Women in Business Programme
Key activities have been performed as following:
Programme Lunch Event was organized in İstanbul on 22.10.2014.
Signed loan agreements under the Programme with Finansbank, Vakıfbank, İşbank and TEB.
Started 54 advisory projects with women-led SMEs and started 5 ongoing business coaching projects.
Nominated, trained and enrolled 10 women entrepreneurs in a one year mentoring programme in partnership with TurkishWIN.
Designed the curriculum for the entrepreneurial skills training courses and contracted for the implementation of eight trainings, two of which have been implemented in Gaziantep.
Designed a diagnostics tool to assess women-led SMEs’ needs for finance and advice.
Continued implementing the communications and visibility plan by organizing regional launch events, regional WiB seminars and an event to celebrate International Women’s Day on 5 March 2015 in Ankara.

## Slide 5: Technical Assistance for Promoting Registered Employment through Better Guidance and Inspection-II
Operation Beneficiary is the Social Security Institution
The Project Budget is € 3.184.702.
The main objectives are:
    to increase the guidance and inspection capacity of SSI both at central and local level,
    to increase the policy making capacity of SSI at central level with regards to the promotion of registered employment,
    to increase the public awareness on the importance of registered employment.
The Inception Report was approved on March 2015. The First Interim Report is in the approval procedure.
Opening Ceremony was held on 21.11.2014.

## Slide 6: Technical Assistance for Promoting Registered Employment through Better Guidance and Inspection-II
  1074 Controllers, Inspectors and Experts from SSI were trained.
  With the awareness raising activities, 535 mukhtars, 450 university students, 123 journalists were reached and given information about the importance of registered employment.
  Academic Advisory Board was established with 23 members including academicians, sector representatives, bureaucrats and judges. 2 out of 6 meetings were completed.
  36 draft sectorial guides were prepared.
  One study visit took place to Austria with the participation of high level bureaucrats.
  Leadership awareness raising conference was held in Bolu with the participation of 180 people from SSI.

## Slide 7: Supply for Promoting Registered Employment through Better Guidance and Inspection-II LOT-2
The Project commenced on 27.06.2014.
The Project Budget is € 997.800
The main purpose with the delivery of equipment to the central and local offices of the SSI is to support the implementation of the new guidance-based approach by increasing the mobility of the SSI personnel.
The Tablet PCs were delivered to 80 cities.
The IT Lot-2 consists of 2000 tablet PC, 35 laptop and 35 printer.
The Provisional Acceptance Certificate was partially approved on November 2014.
The Delivery process for 35 Laptop and 35 Printer is on-going.

## Slide 8: Supply for Promoting Registered Employment through Better Guidance and Inspection-II LOT-1
The Project commenced on 07.01.2015.
The Project Budget is €735.000,00.
The Lot-1 consists of 35 Panelvans which will be delivered to 28 cities.
The main purpose is to support the implementation of the new guidance-based approach by increasing the mobility of the SSI personnel.
The Panelvans will be delivered to 27 cities.
The Delivery Process is on-going.

## Slide 9: Technical Assistance for Increasing Attendance Rates Especially For Girls-II
Operation Beneficiary is Ministry of National Education
The Project Budget is € 4.580.559
The main objective is to enhance investment in human capital by increasing the quality of education, improving the linkage between education and the labour market and raising attendance rates at all levels of education, especially for girls.
  Result 1. Improved institutional capacity of the MoNE, relevant educational institutions and local actors
  Result 2. Raised awareness of school age children, their parents and the whole society in a wider range on the importance of education, especially awareness of girls who have dropped out or have long term non-attendance.
  Result 3. Improved competencies of psychological guidance and counseling staff in order to provide vocational, psychological guidance and counselling services to students and facilitated access of students to the subject services
The Project was started on 23.03.2015.
The approval process of Inception Report is ongoing.

## Slide 10: Supply for Increasing Enrollment Rates Especially for Girls Operation II
The Project Budget is € 2.569.968.
The main purpose is to provide needed equipments in the pilot provinces for secondary education institutions especially those for girls are contributed to girls’ schooling and quality education.
The Provisional Acceptance Certificates of the below mentioned lots were approved as follows;
Lot 1-Soft furniture – 14.04.2015
Lot 2- IT equipment – 05.02.2015
Lot 3- Industrial cooking and cleaning equipment – 29.12.2014
Lot 4- Recreational materials - 29.12.2014
Lot 5- Furniture – 02.04.2015
Lot 6- Sporting goods – 05.06.2015
Lot 7- Electrical appliances – 29.12.2014
Lot 8- Vehicle – 05.03.2015
Lot 9- Stationery equipment – 05.02.2015

## Slide 11: Direct Grant for Strengthening the Impact of the Conditional Cash Transfer Programme in Turkey for Increasing High School Attendance
Operation Beneficiary is Ministry of Family and Social Affairs
Project budget is 35.220.774 €
The project implementation period is 15 months.
The contract signed and the project started on 09.12.2014.
The purpose of this Operation is to provide additional financial support for increasing school attendance rates of high school students in poverty who are potential and current beneficiaries of Conditional Cash Transfer (CCT) Programme with a view to reducing the risk of early school leaving.
Target group: High school students (9th, 10th and 11th grades) who are CCT beneficiaries and potential beneficiaries of the CCT programme in the same grades who are early school leavers, as well as the parents (preferably mothers) of the aforementioned groups.

## Slide 12: Direct Grant for Strengthening the Impact of the Conditional Cash Transfer Programme in Turkey for Increasing High School Attendance (2)
In terms of implementation, € 13.752.420,00 was paid to beneficiaries in 2014 (total number of CCT high school students received payment is 229.207 (The financial incentives in Turkish Liras corresponding to 60 Euro calculated in the date of payment have been paid on 18 December 2014 for each high school CCT beneficiary through the CCT system on the condition of attendance to 9th, 10th and 11th grades).
Launch Event was held on 15th of January 2015 in Ankara with 200 participants.
The Beneficiary submitted the first financial report in December 2014 and the narrative report in January 2015.

## Slide 13: Supply for Improving the Quality of Vocational Education and Training in Turkey
Operation Beneficiary is Ministry of National Education
Project aims to provide necessary equipments to 20 higher vocational school (Ağrı, Bingöl, Bitlis, Çorum, Diyarbakır, Erzincan, Gaziantep, Hakkari, Kahramanmaraş, Kastamonu, Kilis, Mardin, Muş, Ordu, Rize, Siirt, Sivas, Trabzon, Van, Yozgat) and METARGEM to support the quality assurance coordination unit to be established.
Lot 2, Lot 5 and Lot 8 were signed on 19.04.2013 and the implementation started. Final acceptance procedures for the mentioned supply contracts have been completed on 25.02.2015.

## Slide 14: Supply for Improving the Quality of Vocational Education and Training in Turkey (2)
Lot 6, 1 and 4 were signed on 23.12.2014, 26.12.2014 and 06.01.2015 and the implementation started. Provisional acceptance procedures for the following supply contracts is still ongoing:
Lot 1 – Medical Training Equipment
(Budget:677.800,00 €)
Lot 4 – IT and Office Equipment and Electrical Appliances
(Budget:412.672,15 €)
Lot 6 – Kindergarden and Office Furnitures
(Budget:205.000,00 €)

## Slide 15: Direct Grant for Improving the Quality of VET and Vocational Skills of Young People
Operation Beneficiary is Turkish National Agency
The total budget is 25.000.000 €. The project implementation period is 30 months. The contract signed and the project started on 03.12.2014.
The operation is planned to be implemented by way of direct grant based on the idea that the Turkish National Agency is the leading actor in the management of VET mobility projects and the only accredited body of Directorate General of Education and Culture. There are two components: 1. Sub-granting; 2. Institutional Support.
The overall Operation is implemented under HRD OP, whereas the implementation, monitoring and the payment procedures of the component 1, the grant schemes will be managed in accordance with the Erasmus+ Programme rules which are designated by the Erasmus+ Programme Guide and Erasmus+ Guide for National Agencies.

## Slide 16: Direct Grant for Improving the Quality of VET and Vocational Skills of Young People
Direct Grant Contract aims to fund the reserve listed applications of the present 2014 Erasmus+ Call of the National Agency.
Eventually, by 26th December 2014, the NA was able to sign contracts with 314 reserve list projects amounting 23.748.262 Euro.
By 26th December 2014 , 314 grant contacts were signed with sub-grantees and 18.998.609,60 Euro advance payments were made.
Under Institutional Support component, the process for purchase of equipment and supplies and tendering for support staff was finalized.

## Slide 17: Technical Assistance for Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Operation Beneficiary is The Union of Chambers and Commodity Exchanges of Turkey
Total Budget: 4.232.750
Service Contract was finalized on 10.05.2015 and Project Closing Conference was organized in TOBB premises on 5 May 2015.
The training need survey in the 15 Growth Centers, the gap analysis and Mapping Reports, Best Practice Report , an Overall Training Strategy and Action Plan covering each one of the 15 Growth Centers were prepared.
15+1 Awareness Raising Meetings were organised in 15 Growth Centers.

## Slide 18: Technical Assistance for Increasing Adaptability of Employers and Employees to the Changes in Global Economy (2)
10 Training of Trainers session were delivered to 656 people. 2182 employers and 3444 employees were trained in 15 Growth Centers. 5 training sessions were organized in 5 locations for Vocational School Teachers.
10 site visits for employees and employers were organized in developed regions of Turkey with 151 participants. In total 6 study visits in Vienna, Barcelona, Dublin, London, Milan and 10 site visit in western Turkey was organised for employers and employees .
Innovative and sustainable models for 10 SMEs (2 based in each area of responsibility of the TSCCs) which will act as strategic development plans for the ten subject companies and be capable of dissemination among similar businesses as examples of best practice were documented.

## Slide 19: Technical Assistance for Increasing Adaptability of Employers and Employees to the Changes in Global Economy (2)
The 6 TSCC Operational and Business Plans were delivered, to the 5 TSCC Chambers and TOBB. Elaboration of a sustainable institutional and financial model for the TSCCs was documented. 12 TSCC Coordinators were worked in TSCCs during the project implementation period.
An e-Learning platform and online training system is established. 20 e-learning modules were transformed into electronic format. The trainings are created for employers and employees each consisting of 10 modules.
A University-Industry Cooperation Conference was organized in Samsun with cooperation of 19 Mayıs University on 7-8 April 2015.
Project Closing Conference and A Kick of Meeting to lunch 6 KUYAP Training Support and Coordination Centers (TSCCs) in Gaziantep, Elazığ, Sivas, Samsun, Ankara, Erzurum was Organized in Ankara on 5 May 2015.

## Slide 20: Supply for Increasing Adaptability of Employers and Employees to the Changes in Global Economy
The main aim of the Suply Contracts is to provide equipment for 6 TSCC centers.
Provisional Acceptance Certificates for all lots were signed. Final Acceptance Certificate process of lot 1 has been continuing.
Provinces be distributed: Ankara, Elazığ, Sivas, Samsun, Gaziantep, Erzurum.
Lot 1: Office Furniture (Budget:74.297 €)
Lot 2: IT Equipment (Budget: 608.754 €)
Lot 3: Electrical Equipment (Budget:10.907 €)

## Slide 21: Technical Assistance for Increasing Adaptability of Employers and Employees in Tourism Sector
Operation Beneficiary is Ministry of Culture and Tourism
The Project Budget is € 7.558.813
The project implementation period is 30 months (15.01.2014-15.07.2016)
The purpose of the project is to increase the quality and adaptability of employees and employers in the accommodation and food & beverage enterprises in the tourism sector which have MoCT ‘operation and investment licence ; increase training and consultancy capacities of social partners, central and local public organizations/institutions in tourism sector.

## Slide 22: Technical Assistance for Increasing Adaptability of Employers and Employees in Tourism Sector
There are 6 main components of the project;
Awareness Raising Campaign
Labour Force Analysis in the Tourism Sector
Development of Training Programme and Establishment and Implementation of the “Voucher” Programme
Establishment of Networking among Training Providers and Increasing their Training Capacities
Increasing the Awareness on Green Star Certification and Establishment of Centres of Best Practice
Development Of An Online Database System

## Slide 23: Supply for Increasing Adaptability of Employers and Employees in Tourism Sector
The Project Budget is €145.528,00
The project has been finalized by issuing the final acceptance certificates. The final acceptance procedures were finalised on the date of 10.09.2014
Lot 1: Information, Technologies, Electrical and Electronic Equipment
This project provided necessary information technologies, electrical and electronic equipments to 21 Ministy of Culture and Tourism Provincial Directories.

## Slide 24: Supply of Equipment for Increasing the Adaptability of Tradesmen and Craftsmen
Operation Beneficiary is Confederation of Turkish Tradesmen and Craftsmen
Final Acceptance process was completed for Lot 1 , Lot 2 on 07.05.2015 and for Lot 3 on 20.05.2015.
Provisional acceptance process will end on 16 th July of 2015 for Lot 4 and final acceptance process will be started.
Number, titles and Project budgets of Lots were listed below:
- Lot 1 Office Furniture - € 183.170
- Lot 2 IT Equipment - € 146.460
- Lot 3 Woodwork Training Equipment - € 94.920
- Lot 4 Industrial Cooking Equipment- € 44.020

## Slide 25: Technical Assistance for Employment and Social Support Services Coordination and Implementation Model for the Integration of Disadvantaged Persons
Operation Beneficiary is Turkish Union of Municipalities
The Project Budget is €5.999.999.
Objective of the project is; contributing sustainable integration of the disadvantaged persons into the labour market by establishing and implementing a model for coordination and implementation of employment and social support services within the target Municipalities under supervision and guidance of UMT
Target Municipalities are;
http://www.iskep.org.
Bursa Metropolitan Municipality Diyarbakır Metropolitan Municipality Kahramanmaraş Municipality Kars Municipality Kayseri Metropolitan Municipality Şanlıurfa Municipality | Trabzon Municipality Van Municipality Ankara Altındağ Municipality Ankara Keçiören Municipality Mersin Toroslar Municipality Bursa Yıldırım Municipality

## Slide 26: Technical Assistance for Employment and Social Support Services Coordination and Implementation Model for the Integration of Disadvantaged Persons
12 Social Support Service and Employment Guidance Units were established in each Municipality to coordinate employment and socil services in the target municipalities. 12 staff and 2 coordinators were appointed for each SSSEGUs. Monthly work plans for the SSSEGUs are regularly drafted.
All SSSEGU personnel together with the Municipality personnel of related departments are trained,
Software development is completed for the databases on ;
  institutional structures (service providers) at field level
  disadvantaged groups at the selected provinces, and maintaining necessary linkages and flow of information between other institutions’ records

## Slide 27: Technical Assistance for Employment and Social Support Services Coordination and Implementation Model for the Integration of Disadvantaged Persons
Integration of service providers into database process is ongoing. MoFSP, MoNE and İŞKUR dialogue is continuing.
Disadvantaged person data entry process is ongoing. Target is 4750, current figure is 900.
Study visits are conducted to Portugal and Croatia.
Conducted local seminars to eliminate prejudices against the disadvantaged
Local Media Seminars in Bursa, Kars, Kahramanmaraş, Kayseri, Şanlıurfa, Trabzon, Van and Mersin Toroslar.
Informative Seminars for the personnel of each beneficiary Municipality on social integration of disadvantaged persons
National level experience sharing meetings (First meeting-presenting experiences in inclusion of persons with disabilities from Germany, Italy and Portugal)

## Slide 28: Facilitating Access of Disadvantaged Higher Education Students to Labor Market Including Scholarship Support - 2nd Phase
Operation Beneficiary is YURTKUR
The total budget of the second phase is 15.000.000 €.
The target groups are students who are in poverty or at risk of poverty and in their last credit receiving year.
18.400 students received scholarship in 2014-2015 Academic Year.
  7461 male students in undergraduate
  7413 female students in undergraduate
  2452 male students in associate degree
  2597 female students in associated degree
18.400 students received 330 TL each month and in total 2.640 TL for 8 months.

## Slide 29: Direct Grant for Supporting Registered Employment of Women Through Home-Based Child Care Services
Operation Beneficiary is Social Security Institution
Budget of the project is 39.625.600,00 €. The contract signed and the project started on 05.03.2015 with implementation period of 24 months.
Operation mainly aims to increase the registered employability of women.
Target groups of the operation are women with children up to 2 years of age who are working or about to start/return to working in a registered job and women providing or to start providing home-based child care services as a registered job.
5.000 mothers and 5.000 child care-givers will benefit from the project in 3 pilot provinces (İzmir, Bursa and Antalya)

## Slide 30: Direct Grant for Supporting Registered Employment of Women Through Home-Based Child Care Services
The amount of the financial support is € 300 per month. The amount of support will be applied by 30% higher in cases where the mother employs a child caregiver with a childcare certificate approved by the MoNE or İŞKUR; or she has a child with at least 40 % of disability.
The operation will be implemented through four main stages:
  Information and publicity,
  Receiving applications,
  Monthly evaluations, payments and monitoring
  Ex-post controls and verifications.
With the participation of the Minister of Labour and Social Security the opening conference was held on 15.04.2015. Information and publicity stage has been performed with the publicity events in Bursa, Antalya and İzmir.
In June 2015 the applications of the mothers will be started to be received.

## Slide 31: Grant Scheme - Improving the Quality of Vocational Education and Training in Turkey II
70 grant projects with a total budget of € 14.649.850,87 were signed on 14th July 2014 and 15th July 2014 and the implementation process started on 1st September 2014 for all contracts.
Contracts of 2 grant projects were terminated due to lack of possibility to effectively implement the project activities. Total budget of € 488.607 is recalled for those contracts.
Interim reports consisting of narrative and financial sections of 67 projects were received in the deadline of 15th of April 2015. Technical and financial verification process of the reports are ongoing. Only 1 project did not submit its interim report and the contract is in the process of possible termination.
There have been suspicious irregularities during the implementation of the projects and all of them are timely reported to the irregularity officer.
In general, substantial part of the projects is implemented successfully so far.

## Slide 32: Grant Scheme - Improving the Quality of Vocational Education and Training in Turkey II
Monitoring System of the İKGPRO is well implemented so far. There is a need for strengthened cooperation with the Operation Beneficiaries to prepare grant inception reports, conduct thematic controls and reports. Contracting Authority is aware the needs of the Operation Beneficiaries to perform their thematic control mission and takes relevant measures to assist OBs.
Monitoring System of the İKGPRO is very much praised by the EU auditors during their mission for the entrustment process.
MİSTİK worked very effective and efficient manner so far for the grant beneficiaries, Operation Beneficiary and the Contracting Authority. Thousands of questions and requests were processed through MİSTİK system.
12 monitoring experts were well deployed to the projects and assisted the beneficiaries in 7/24 hours principle. 8 Contract Managers were settled in decision making and verification position.

## Slide 33: Grant Scheme - Improving the Quality of Vocational Education and Training in Turkey II
In total 303 monitoring visits and on the spot checks are realized for the grant projects.
All projects were visited with thematic control experts to evaluate the capacity- quality and content of the activities and increase the level of knowledge and awareness of grant beneficiary regarding to thematic issues between 16.06.2014 and 04.07.2014.
The first technical monitoring visits to 70 grant projects were conducted by the Monitoring Experts between the dates of 01.09.2014 - 30.09.2014. After the first half of the project implementation period, the second technical monitoring visits were realised between 05.02.2015 - 10.03.2015.
Furthermore, the Contract Managers visited the projects (18.05.2015 – 04.06.2015) in the scope of the “on-the-spot check visits”. Those on the spot check visits aims to control the activities implemented under the projects and warn the grant beneficiaries in the light of the findings for the interim reports received by the Contracting Authority on 15.04.2015.

## Slide 34: Thank You for Your Kind Attention and Patience