## Slide 1: HRDOP IN IMPLEMENTATION Quick Summary of Achievements
Presented by Project Management Unit
25.06.2013

## Slide 2: Achieved Cornerstones via Ongoing Operations

## Slide 3: List of Ongoing Operations
Measure 1.2: Promoting Youth Employment
Measure 1.4: Improving the Quality of Public Employment Services
Measure 2.1: Increasing Enrolment Rates Especially For Girls In Secondary Education
Measure 2.2: Improving the Quality of Vocational and Technical Education in Turkey
Measure 3.1: Promoting Life Long Learning
Measure 3.2: Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Measure 3.2: Increasing Adaptability of Employers and Employees in Tourism Sector
Measure 5.1: Implementation of Human Resources Development Operational Programme
Measure 5.2-5.3:Potential Operation and Grant Beneficiaries, Information and Publicity

## Slide 4: Measure 1.2: Technical Assistance for Promoting Youth Employment
Completion of the survey with the companies (1080 firms) in 15 growth centres addressing the investment areas with high competitiveness in each province
Completion of the list of the national and international financial means which the young people can use to set up a business
Preparation of «Entrepreneurship Guidelines for the Young People»
Completion of the organization of entrepreneurship and career days in 11 growth centres
Preparation of a web-site including all the information regarding entrepreneurship
http://www.gencistihdami.net

## Slide 5: Technical Assistance for Promoting Youth Employment (2)
Completion of the design of the «Youth Entrepreneurship Support Model»
Delivery of the entrepreneurship trainings in 5 pilot provinces
Completion of workshops regarding action plans for youth employment in 4 pilot provinces
Preparation of a compendium regarding grant scheme results
    http://www.gencistihdami.net

## Slide 6: Measure 1.4 Technical Assistance for Improving The Quality of Public Employment Services
Completion of the preparation of Model Office Action Plans in 43 provinces
Completion of trainings regarding Model Office approach at the provincial level to the staff in 43 provinces
Completion of the preparation of a methodology on conducting labour market analyses and delivering the training to the staff of the Beneficiary at the local and central level
Completion of study visits regarding job and vocational guidance services
Publication of guidelines including information on public employment services
http://www.kip.org.tr

## Slide 7: Technical Assistance for Improving The Quality of Public Employment Services (2)
Completion of the design of a model to monitor the active labour market policies provided by the Beneficiary
Completion of Communication Campaign II
Completion of short films on introduction and selection of occupations
Completion of trainings regarding the employment policy making
Provision of membership to certain databases for accessing journals in the field of social policy and employment
Completion of internships regarding employment policy making in European Agencies and relevant institutions for 13 staff from the Beneficiary and the MoLSS
http://www.kip.org.tr

## Slide 8: Supply for Improving The Quality of Public Employment Services
Provisional acceptance procedures for the supply contract of
Lot 1: Office Furniture has been almost completed

## Slide 9: Measure 2.1
Completion of Main Research Report which combined the Provincial Research Report regarding the ways of enrollment of girls
Completion of the action plans of the provinces including the activities on taking measures locally about the dropout and enrolment problems and the importance of education
Organization of a 1-day information meeting organized to inform the social partners, media representatives and NGOs on the research results and the implementation of the action plans in Ankara with the participation of 150 people
Completion of trainings for 180 formator teachers about the psychological guidance
Conduction of 3 study visits to Germany, Austria and United Kingdom
http://kizlarinegitimi.meb.gov.tr
Technical Assistance for Increasing Enrollment Rates Especially for Girls

## Slide 10: Technical Assistance for Increasing Enrollment Rates Especially for Girls (2)
Completion of the procurement process of the incentives to girls such as boots, coats, school bags, stationery equipment for 2000 children
Completion and distribution Access to Education Opportunities Booklet in 20000 copies
Completion of 4 spot films, 2 short films, and 1 radio spot in order to prompt and increase girls' school enrolment rate and also to raise consciousness
Publication of the compendium book identifying the best practices among the awarded projects, include the synopsis of the all projects and their results in 500 copies,
Conducting face to face interviews (house visits) to at least (final target) 3.200 families in 16 pilot provinces by the trained teachers
Organization of the National Conference in Şanlıurfa and International Conference in İstanbul
http://kizlarinegitimi.meb.gov.tr

## Slide 11: Supply for Increasing Enrollment Rates Especially for Girls Operation
Provisional Acceptance process for five lots is ongoing:
Lot 1 - Information Technology Equipment
Lot 3 - White Goods Equipment
Lot 5 - Food Technology Equipment
Lot 6 - Cosmetics And Hair Care Services Equipment
Lot 7 - Food And Beverages Services Equipment (Kitchen)

## Slide 12: Technical Assistance for Improving the Quality of Vocational Education and Training in Turkey
Establishment of working relationships between TAT and counterparts.
Identification of social partners and engaging in project.
Assessment of a sample of schools undertaken and production of situation analysis
Commencement of drafting national quality assurance strategy system concept paper.
Developing Self-Evaluation Manual and NQAS Manual
Delivery of trainings for self-evaluation component of NQAS in all 50 pilot institutions.
Preparation of vocational maps in 22 fields and 91 occupational analyses.
http://metek.meb.gov.tr
Measure 2.2

## Slide 13: Supply for Improving the Quality of Vocational Education and Training in Turkey (2)
Three Lots were signed on 19.04.2013 and the implementation started.
Lot 2 – Farming, Animal Care and Food Processing Equipment
Lot 5 – IT and Office Equipment and Electrical Appliances
Lot 8 – Mechanical Manufacturing Equipment

## Slide 14: Measure 3.1 Technical Assistance for Promoting Life Long Learning
Preparation of final draft Law for the Co-ordination of Lifelong Learning,
Preparation of Draft National Strategy for Lifelong Learning 2014-2018,
Preparation of Draft Framework for Recognition of Prior Learning,
Preparation of Draft Provincial Lifelong Learning Action Plans,
Development of National Lifelong Learning Web Portal,
http://hayatboyu.meb.gov.tr

## Slide 15: Technical Assistance for Promoting Life Long Learning (2)
Establishment of interface between modules and learning outcomes in 7 occupational areas,
Completion of training programme to develop local capacity in lifelong learning,
Completion of training programme in monitoring and evaluation,
Completion of 7 study visits regarding LLL, ECVET and RPL,
Completion of 4 spot films and 1 promotional film.
http://hayatboyu.meb.gov.tr

## Slide 16: Supply Contract for Promoting Life Long Learning Operation
Provisional acceptance procedures for the following supply contracts have been completed:
Lot 1: Office Furniture
Lot 2: IT Equipment, Hardware and Software

## Slide 17: Measure 3.2 Technical Assistance for Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Completion of review of the stakeholders in the regions and the previous relevant projects
Preparation of the training need survey in the 15 Growth Centres
Designing and preparation of the best practice survey in the developed Turkish regions
Establishment and maintenance of website

## Slide 18: Supply for Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Two contracts below mentioned were signed and the process of provisional acceptances are ongoing for both contracts:
Lot 1: Office Furniture
Lot 3: Electrical Equipment

## Slide 19: Measure 3.2 Supply for Increasing Adaptability of Employers and Employees in Tourism Sector
Delivery, installation putting into operation, inspection and testing of the equipment have been completed, provisional acceptance procedures are ongoing.
Lot 1: Information, Technologies, Electrical and Electronic Equipment

## Slide 20: Measure 5.1 Technical Assistance for Implementation of Human Resources Development Operational Programme
Delivery of the following trainings;
  Introduction trainings for newly recruited staff
  Irregularities, internal control and risk management
  Grant and framework evaluation, tender evaluation
  Monitoring and management verification
  Eligibility of expenditures and rules of payment process
  Financial planning and expenditure verification
  Mainstreaming strategy
  PRAG
  Sampling methodologies
  Web design, excel, outlook and MS project

## Slide 21: Technical Assistance for Implementation of Human Resources Development Operational Programme (2)
Completion of the study visits in order to give an insight on funds management of the country visited and allowing for the members of each unit in IPA MD to exchange experiences on below areas;
  Program management and procurement process
  Project management
  Financial management
  Quality assurance and coordination processes
  IT applications
Establishment and Improvement of MIS systems.
Full time consultancy support to İKGPRO
Evaluation of HRD OP process has been initiated.

## Slide 22: Supply Contract for Implementation of Human Resources Development Operational Programme
The project has been finalized by issuing the final acceptance certificates. Dates of the final acceptances are as follows:
Lot 1 – 07.05.2013
Lot 2 – 15.05.2013
Lot 3 and Lot 5 – 08.05.2013
Lot 4 – final acceptance procedures are ongoing
Lot 6 – 05.04.2013

## Slide 23: Measure 5.2-5.3 Technical Assistance for Potential Operational and Grant Beneficiaries, Information and Publicity
Revision of HRD OP Mainstreaming Strategy in line with the comments and feedback of the HRD OS Units and Beneficiaries.
Delivery of an introductory training and Concept Note training to Roma NGOs
Delivery of Training and Direct Expert Support regarding OIS, ToR, Grant Guideline, Operation and Project preparation to Operation Beneficiaries and Operating Structures
Organization of an info-consultation meeting for potential applicants of the Call for Operations launched by the HRD OS

## Slide 24: Technical Assistance for Potential Operational and Grant Beneficiaries, Information and Publicity (2)
Organization of Info Days in more than twenty cities regarding HRD OP Grant Scheme, EU funds and EU Institutions
Delivery of ‘Information and Visibility’ training to all potential OBs
Organization of Awareness raising activities for the launch of the Call for Operations and also for the launch operation of YURTKUR
Publication and distribution of 3 HRD OP Magazine
Publication and distribution of HRD OP Priority Axis Booklet and IPA HRD OP Brochure
Utilization of ‘Media monitoring’ for our project activities to ensure capturing all occasions where project related news appear in newspapers, TV, radios, etc.

## Slide 25: Highlights in Recently Completed Operations

## Slide 26: Measure 1.1: Technical Assistance for Promoting Women Employment
The most successful one of the newly developed methods was women job clubs. Job clubs provide intensive motivation and support for longer-term unemployed people. After 3 weeks of involving in the clubs, 60 % of the participants received a job offer and %50 of the participants has started to work.
Client Referral Network was developed as the most relevant ALMP model for overcoming multiple obstacles for female labor force participation. Several seminars were organized for İŞKUR staff and relevant partner institutions to present, improve and develop the model. Model was tested through trainings and services delivered to women target groups.
      www.kadinistihdami.net

## Slide 27: Measure 1.3 Technical Assistance for Promoting Registered Employment
The most successful action of the project was the trainings given to many stakeholders such as MoLSS, IŞKUR, SSI, other public institutions and social partners including associations (TESK, TOBB, etc.). Those trainings made a major contribution to the capacity building of those partners especially inspectors of SSI.1456 staff of SSI, MoLSS, ISKUR, other relevant social partners were trained thanks to those trainings of the project.
    http://www.kit-up.net