## Slide 1: HRDOP IN IMPLEMENTATION Quick Summary of Achievements
Project Management Unit
26.11.2014

## Slide 2: List of Ongoing Operations
Measure 1.1: Woman in Business
Measure 1.3 Promoting Registered Employment through Better Guidance and Inspection-II
Measure 2.1: Increasing Enrolment Rates Especially For Girls In Secondary Education-II
Measure 2.2: Improving the Quality of Vocational and Technical Education in Turkey
Measure 3.2: Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Measure 3.2: Increasing Adaptability of Employers and Employees in Tourism Sector
Measure 3.2: Increasing Adaptability of Tradesmen and Craftsmen
Measure 4.1: Employment and Social Support Services Coordination and Implementation Model for the Integration of Disadvantaged Persons

## Slide 3: Measure 1.2: Woman in Business Programme
The overall objective of the Programme is to promote women's entrepreneurship in Turkey, and women’s participation in business, by assisting women-led small and medium-sized enterprises to access finance, know-how and non-financial business development services.
Total budget of the programme: 38.000.000 €
The purpose of the Programme is to:
Support women-led small and medium sized enterprises (SMEs) in accessing finance for their sustainable growth and job creation
Develop sustainable credit mechanisms targeted to women-led SMEs through technical assistance to participating financial institutions
Support women-owned and women-managed SMEs in accessing know-how, non-financial business development services and networking opportunities.
Help improve human resources at women-led SMEs.

## Slide 4: Measure 1.2: Woman in Business Programme
The Programme will provide:
Minimum of 12,000 sub-loans will disperse for women-led SMEs
More than 2,000 women entrepreneurs will be provided with basic diagnostic services identifying their business’ financing and know-how needs
640+ women will be trained through entrepreneurial skills courses
250+ women-led enterprises will receive business advice and industry expertise
90+ women-led enterprises will participate in ongoing business coaching projects
80+ women-led enterprises will connect with peers through the mentoring programm
In total more than 15,000 women entrepreneurs will be supported.

## Slide 5: Technical Assistance for Promoting Registered Employment through Better Guidance and Inspection-II
The Project Budget is € 3.184.702.
The main objectives are:
  to increase the guidance and inspection capacity of SSI both at central and local level,
  to increase the policy making capacity of SSI at central level with regards to the promotion of registered employment,
  to increase the public awareness on the importance of registered employment.
The Project was started on 15.09.2014.
The Project is in the Inception Phase.
Opening Ceremony will be held on 21.11.2014.

## Slide 6: Supply for Promoting Registered Employment through Better Guidance and Inspection-II
The Project Budget is € 997.800
The tablet were delivered to 80 cities.
The main purpose with the delivery of equipment to the central and local offices of the SSI is to support the implementation of the new guidance-based approach by increasing the mobility of the SSI personnel.
The Project started on 27.06.2014.
The IT Lot consists of 2000 tablet PC, 35 laptop and 35 printer.
The Provisional Acceptance Certificate was approved.

## Slide 7: Supply for Increasing Enrollment Rates Especially for Girls Operation II
Operation Beneficiary is The Ministry of National Education.
The Project Budget is € 2.569.968.
The main purpose is to provide needed equipments in the pilot provinces for secondary education institutions especially those for girls are contributed to girls’ schooling and quality education.
There are 9 lots in the operation. The contract for Lots 8 was signed on 05.09.2014. The other contracts of Lot 1, 2, 3, 4, 5, 6, 7 and 9 were signed on 08.09.2014.
The kick-off meeting for lots 2, 3, 4, 5, 7, 8 and 9 were held on 18.09.2014. For lots 1 and 6, the kick-off meeting was held on 27.09.2014. The Operation Beneficiary and the contractors were informed by OS regarding the relevant procedures.

## Slide 8
The number and titles of lots which were signed are indicated below:
Lot 1-Soft furniture
Lot 2-IT equipment
Lot 3-Industrial cooking and cleaning equipment
Lot 4-Recreational materials
Lot 5-Furniture
Lot 6-Sporting goods
Lot 7-Electrical appliances
Lot 8-Vehicle
Lot 9-Stationery equipment

## Slide 9: Technical Assistance for Improving the Quality of Vocational Education and Training in Turkey
The Project Budget is € 5.983.088
The project implementation period is 31 months (22.05.2012-21.12.2104)
Completion of developing and piloting a National Quality Assurance System in line with European Quality Assurance Reference Framework for VET
Completion of National Quality Assurance Strategy System Concept paper
Completion of analyzing and revising the legislation to provide an active collaboration between the labour market and vocational education institutions
Completion of vocational maps in 22 fields and 91 occupational analyses
Commencement of testing of the developed/revised modular based curricula in the selected 16 pilot secondary and 11 pilot higher VET schools
Completion of developing Self-Evaluation Manual and NQAS Manual
http://metek.meb.gov.tr
Measure 2.2

## Slide 10: Technical Assistance for Improving the Quality of Vocational Education and Training in Turkey (2)
Completion of trainings for self-evaluation component of NQAS in all 50 pilot institutions
Completion of trainings for administrators and teacher about the pedagogical and professional competences
Revision the curricula according to feedbacks taken during the implementation of curricula
Organization of a study visit to examine the best practices
Preparation of a periodical and a cinevision
Organization of Closing Conference
http://metek.meb.gov.tr
Measure 2.2

## Slide 11: Supply for Improving the Quality of Vocational Education and Training in Turkey
This project will provide necessary equipments to 20 higher vocational school (Ağrı, Bingöl, Bitlis, Çorum, Diyarbakır, Erzincan, Gaziantep, Hakkari, Kahramanmaraş, Kastamonu, Kilis, Mardin, Muş, Ordu, Rize, Siirt, Sivas, Trabzon, Van, Yozgat) and METARGEM to support the quality assurance coordination unit to be established.
Lot 2 – Farming, Animal Care and Food Processing Equipment (Budget:188.599,00 €)
Lot 5 – IT and Office Equipment and Electrical Appliances
(Budget:319.339,00 €)
Lot 8 – Mechanical Manufacturing Equipment
(Budget:265.065,36 €)
PAC is issued

## Slide 12: Grant Scheme - Improving the Quality of Vocational Education and Training in Turkey
Grant contracts were signed on 14th July 2014 and 15th July 2014 and the implementation process started on 1st September 2014 for all contracts.
70 grant projects with a total budget of € 14.649.850
All of them were visited with thematic control experts to evaluate the capacity- quality and content of the activities and increase the level of knowledge and awareness of grant beneficiary regarding to thematic issues between 16.06.2014 and 04.07.2014.
Between 01.09.2014- 30.09.2014 a total of 70 technical monitoring visits have been made by the Monitoring Experts.
Measure 2.2

## Slide 13: Grant Scheme - Improving the Quality of Vocational Education and Training in Turkey (2)
The distribution of Grant Contracts by regions:
Central Anatolia: 27 %
Black Sea: 16 %
SouthEast Anatolia:15 %
East Anatolia:15 %
Marmara:11 %
Aegean:8 %
Mediterranean:7 %
Measure 2.2

## Slide 14: Measure 3.2 Technical Assistance for Increasing Adaptability of Employers and Employees to the Changes in Global Economy
Total Budget: 4.232.450
Implementation period: 11.02.2013 – 11.05.2015( 27 months)
The training need survey in the 15 Growth Centers was prepared
15+1 Awareness Raising Meetings were organised in 15 Growth Centers
Project website was established and in use
A 5 minute video of the projects activities was prepared
Project Booklet and other visibility and merchandising materials prepared and distributed
The Chambers Capacity Mapping Document and the Best practices in Western Turkey Report were prepared
5 Capacity Building programmes for TSCC Coordinators for accreditation were delivered
Training materials was prepared and the trainings are still on going.
10 Training of Trainers Conference were delivered in Ankara
4 study visits for employers and employees was organised in Dublin, Barcelona and Vienna

## Slide 15: Measure 3.2 Supply for Increasing Adaptability of Employers and Employees to the Changes in Global Economy
The main aim of the Suply Contracts is to provide equipment for 6 TSCC centers.
Two contracts Lot 1 and Lot 3 were signed and the process of provisional acceptance was done.
Lot 2, Supply of IT equipment was signed on 19.09.2014.
Lot 1: Office Furniture (Budget:74.297 €)
Lot 2: IT Equipment (Budget: 608.754 €)
Lot 3: Electrical Equipment (Budget:10.907 €)
Provinces be distributed: Ankara, Elazığ, Sivas, Samsun, Gaziantep, Erzurum

## Slide 16: Measure 3.2 Technical Assistance for Increasing Adaptability of Employers and Employees in Tourism Sector
The Project Budget is € 7.558.813
The project implementation period is 30 months.(15.01.2014-14.06.2016)
Establishment of working relationships between TAT and counterparts
Identification of social partners and completion of Communication Strategy
Completion of labour force analysis implementation strategy and survey methodology
http://tuyup.turizm.gov.tr

## Slide 17: Measure 3.2 Technical Assistance for Increasing Adaptability of Employers and Employees in Tourism Sector(2)
Completion of pilot phase of voucher programme
Preparation of Pilot Phase Evaluation Report
Designing and preparation of training of trainers programme
Preparation of business requirement analysis report for green star application
Completion of 10 green star certification programme seminars
Development and maintenance of an online database system
Preparation of draft labour force analysis and training needs analysis questionnaires
http://tuyup.turizm.gov.tr

## Slide 18: Measure 3.2 Supply for Increasing Adaptability of Employers and Employees in Tourism Sector
The Project Budget is €145.528,00
The project has been finalized by issuing the final acceptance certificates. The final acceptance procedures were finalised on the date of 10.09.2014
Lot 1: Information, Technologies, Electrical and Electronic Equipment
This project provided necessary information technologies, electrical and electronic equipments to 21 Ministy of Culture and Tourism Provincial Directories.

## Slide 19: Measure 4.1 Technical Assistance for Employment and Social Support Services Coordination and Implementation Model for the Integration of Disadvantaged Persons
The contract was signed on 20.05.2014.
The Project Budget is €5.999.999.
The Project implementation period is 23 months.
The key experts were selected before the start of the implementation according to TOR.
The implementation of the contract was started on 19.08.2014.
The kick off meeting for the Contract was held on 25.08.2014.
A meeting was held with targeted municipalities on 08.09.2014.
Under Activity 1.1, “Functions and responsibilities” Document including reporting requirements for «Social Service Support and Employment Guidance Units» and Job Descriptions of the personnel was revised.
İSKEP

## Slide 20: Measure 5.1 Technical Assistance for Implementation of Human Resources Development Operational Programme
The Project Budget is €3.709.135.
The project implementation period is 36 months.
Increased institutional, technical and administrative capacity of MoLSS, EU Coordination Department for:
  Project preparation, implementation, monitoring, evaluation, quality assurance and control, tendering, contracting, financing and accounting and improvement of its functions.
Increased institutional, technical and administrative capacity of the Internal Audit Unit for audit and guiding functions.
Provided contributions for establishing an institutional training policy.

## Slide 21: Technical Assistance for Implementation of Human Resources Development Operational Programme (2)
Ensured smooth implementation of the HRD OP as regards programming, contract management, monitoring, evaluation, quality control and assurance.
Set necessary administrative and procedural requirements in place for the MoLSS, EU Coordination Department in order to pass to decentralized implementation system without ex-ante controls.
A well-functioning MIS and website is in place.
8 study visits.
860 trainees in 52 workshops and sessions.

## Slide 22: Technical Assistance for Potential Operational and Grant Beneficiaries, Information and Publicity
The Project Budget is €5.368.570.
The Project implementation period is 36 months.
Support for development of absorption capacity of final beneficiaries: Operation Beneficiaries, including Central Grant Monitoring Teams and Regional Grant Monitoring and Technical Assistance Teams, and Grant Beneficiaries
Organization of 56 Info Days for 5 grants schemes.
Publication and distribution of 20.350 brochures and 13.600 technical leaflets
9575 trainees in 197 workshops and sessions regarding OIS, ToR, Grant Guideline, Operation and Project preparation, Visibility, PCM, TS&MR, Concept Note etc. to Operation Beneficiaries, Grant Beneficiaries and Operating Structures.
6 successful Study Visits.

## Slide 23: Thank You